## Guide
Risk register
Risk register: the qualitative risk register of Project Risk Analysis as a workbook. Fill it in here or in the app, then open it in the app with Open... in step 01 Setup or 02 Identify.
How to use it
1. Matrix | Check the matrix first: the probability bands, the severity levels and areas, and the Red, Amber and Green rating grid. The dropdowns on the Risks sheet come from it.
2. Risks | One row per risk. Write it as cause, event and effect. Leave the ID empty and the app gives the risk the next free ID (R01, R02...).
3. Assessments | For each of Inherent, Current and Target, choose the probability letter and a severity level on each area that applies; leave an area empty when it does not. The Rating column works out Red, Amber or Green from the Matrix sheet.
4. Actions | One row per action on the Actions sheet, with the ID of its risk.
5. Open in the app | Save as .xlsx, then Open... in step 01 Setup or 02 Identify. Opening replaces the register in the app. The app reads the file in your browser: nothing is uploaded.
What the app checks
Values | Type, Status, Response and the Actions' Status must be one of the dropdown's values (any capitals). Probability letters must be bands of the matrix and severities its levels. Dates are date cells, or text as yyyy-mm-dd. A value it cannot read stops the file opening, with the sheet, row and column named.
Approval | An approved risk needs a title and an event. Approved risks are closed, not deleted, so the register keeps its history.
Promote | Approved risks at or above the promote rule on the Matrix sheet go on to the model at Promote, with the Model link columns (activities, and any probability or impact set by hand).
Ratings | The Rating columns are worked out by Excel for your convenience; the app works every rating out again from the matrix.
Risks sheet
ID | The risk's ID, unique in the register. Empty: the next free ID.
Title, Cause, Event, Effect | "Because of (cause), (event), which would lead to (effect)." Title and Event are needed to approve the risk.
Category | One of the categories on the Matrix sheet.
Type | Threat or Opportunity.
Status | Proposed, Approved, Rejected or Closed. Empty: Proposed.
Raised by, Raised, Owner | Who raised the risk and when, and who owns it.
Probability | Under Inherent, Current and Target: the probability band's letter.
Severity areas | One column per area of the matrix: the severity level (I, II...) on that area, or empty. The risk's severity is its worst area.
Response | Threats: Avoid, Transfer, Mitigate or Accept. Opportunities: Exploit, Share, Enhance or Accept. With its description and cost.
Model activities | The P6 activity IDs the risk would delay, separated by commas.
Always promote | Yes to promote the risk to the model even below the promote rule (it must still be approved).
Impact units | days (working days) or percent (of each activity's remaining duration), for impacts set by hand.
By hand | Probability, impact distribution (triangle, pert or uniform) and min, most likely and max, before and after mitigation, to replace what Promote works out from the matrix. Leave them empty to use the matrix.
Actions sheet
Risk ID, Action | The risk the action belongs to, and what is to be done.
Owner, Due, Status | Who does it, by when (a date), and Open, Done or Cancelled. An open action past its due date is overdue.

## Risks
Risk | [10 empty] | Inherent: before any controls | [7 empty] | Current: with today's controls | [7 empty] | Target: after the response | [7 empty] | Response |  |  | Model link (optional): how the risk goes into the model at Promote
ID | Title | Cause | Event | Effect | Category | Type | Status | Raised by | Raised | Owner | Probability | Schedule | Cost | Quality and performance | Health and safety | Environment | Regulatory | Rating | Probability | Schedule | Cost | Quality and performance | Health and safety | Environment | Regulatory | Rating | Probability | Schedule | Cost | Quality and performance | Health and safety | Environment | Regulatory | Rating | Response | Response description | Response cost | Model activities | Always promote | Impact units | Probability (by hand) | Impact distribution | Impact min | Impact most likely | Impact max | Mitigated probability (by hand) | Mitigated distribution | Mitigated min | Mitigated most likely | Mitigated max

## Actions
Risk ID | Action | Owner | Due | Status

## Matrix
Risk matrix
The matrix the risks are rated on, as in step 01 Setup. Change it here or in the app. Keep each block's title in column A and its header row as they are; a blank row ends a block.
Settings
Setting | Value | Notes
Register name | Risk register | Shown on the reports.
Currency |  | For response costs and the cost of delay, for example INR or USD.
Cost of delay per working day | 0 | Value of one working day of delay to the project finish, for the cost-benefit of responses. 0 = not set.
Promote at or above rating | Amber | Risks rated at or above this go on to the model at Promote: Red, Amber or Green.
Promote on severity area | schedule | The area that measures delay (its id in Severity areas).
Promote at or above severity | II | Only risks at or above this level on that area can delay the schedule.
Probability bands | Least likely first, without overlaps. From and To are percentages.
Letter | Label | From | To | Guidance
A | Remote | 0% | 5% | Not expected; it could happen only in exceptional circumstances. Recorded for completeness.
B | Unlikely | 5% | 25% | Not likely on this project, although it has happened elsewhere in the industry.
C | Occasional | 25% | 50% | It may well not happen, but it has happened from time to time and is a credible possibility here.
D | Likely | 50% | 70% | It has happened on similar projects and is more likely than not to happen on this one.
E | Most likely | 70% | 95% | It can reasonably be expected to happen on this project.
Severity levels | Numbered I, II, III... from the least severe. The Level column is renumbered when the app writes the file.
Level | Name
I | Insignificant
II | Minor
III | Significant
IV | Major
V | Very high
Rating grid | Rows: probability, most likely at the top. Columns: severity. Each cell is rated Red, Amber or Green.
Probability | Label | I Insignificant | II Minor | III Significant | IV Major | V Very high
E | Most likely | Green | Amber | Amber | Red | Red
D | Likely | Green | Green | Amber | Amber | Red
C | Occasional | Green | Green | Amber | Amber | Amber
B | Unlikely | Green | Green | Green | Amber | Amber
A | Remote | Green | Green | Green | Amber | Amber
Severity areas | An area with a Unit is measured: give its ranges under Severity ranges. Without a Unit it is described in words.
Id | Name | Unit | I | II | III | IV | V
schedule | Schedule | % of planned project duration | No delay to the finish; absorbed by the available float | Delay of less than 3% of the planned project duration | Delay of 3% to 6% of the planned project duration | Delay of 6% to 10% of the planned project duration | Delay of more than 10% of the planned project duration
cost | Cost | % of approved control budget | Up to 0.25% of the approved control budget | 0.25% to 0.5% of the approved control budget | 0.5% to 1% of the approved control budget | 1% to 2% of the approved control budget | More than 2% of the approved control budget
quality | Quality and performance |  | No effect on objectives or on how users see the result | Slightly below expectations but within acceptable limits; users may notice | Outside acceptable limits; users are dissatisfied and cost or time are affected | Well outside the limits; substantial rework and changes are needed | Unacceptable; failure could cause a major loss of business
safety | Health and safety |  | No injury of note and no working time lost | A minor injury to one person; work continues | Injuries to one or more people with substantial working time lost | A fatality or serious injuries, or work largely stopped; an investigation is likely | More than one fatality; legal action against the company is likely
environment | Environment |  | No environmental damage of note | Minor damage, contained on site and put right; no adverse publicity | Moderate damage near the project that can be put right, at some cost or delay | Major damage the company cannot put right alone, with substantial cost, delay and adverse publicity | Severe damage that could make the project unviable and bring heavy penalties
regulatory | Regulatory |  | A minor lapse, put right by declaration | Minor non-compliance; small penalties or some media attention possible | Significant non-compliance; substantial penalties or adverse publicity likely | Major non-compliance; heavy penalties or a temporary stop to work possible | Extensive non-compliance; work could be stopped indefinitely
Severity ranges | In the area's unit. Leave To empty on the highest level for "and above".
Area | Level | From | To
schedule | I | 0 | 0
schedule | II | 0 | 3
schedule | III | 3 | 6
schedule | IV | 6 | 10
schedule | V | 10 | 20
cost | I | 0 | 0.25
cost | II | 0.25 | 0.5
cost | III | 0.5 | 1
cost | IV | 1 | 2
cost | V | 2
Rating guidance
Rating | Label | Actions (one per line)
Red | Red | Not tolerable: act now to reduce it Report to senior management at every review Give it an owner and focused actions with dates
Amber | Amber | Significant: strengthen the existing controls Track the actions and check that they work
Green | Green | Low: keep the existing controls in place Watch it and escalate it if it gets worse
Categories
Category
Design
Procurement
Construction
Commissioning
Commercial
Regulatory
Health and safety
Environment
External